## 00 Overview
Bus Charging Scheduler — Build Plan & Task Tracker
Tick the ✓ Done column on any task sheet. Progress Dashboard updates automatically. Deadline: June 2.
How to use the check-off system
1. Mark a task done | On '01 Master Backlog' (and the AI Prompts / Architecture / Deployment sheets), click the ✓ Done cell and pick ✓ from the dropdown. The whole row turns green and strikes through.
2. Track status | Use the Status dropdown (Not Started / In Progress / Blocked / Done) for finer state.
3. Watch progress | 'Progress Dashboard' shows overall %, per-epic %, and per-priority completion — all live formulas.
4. Full PDF coverage | Every requirement from the 13-page PDF is captured: 50 tasks + 47 traced requirements. See 'Requirements Trace'.
Tip (Excel 365) | You can also use Insert ▸ Checkbox on the ✓ column if you prefer native checkboxes; the dropdown method works in Excel, Google Sheets and LibreOffice.
Sheets
Sheet | What it contains
Progress Dashboard | Live completion %: overall, per epic, per priority
01 Master Backlog | 50 tasks — ✓ Done + Status, AI-ready prompts, deps, effort, spec ref
02 Requirements Trace | All 47 PDF requirements mapped to tasks (full-PDF proof)
03 Jira Backlog | Epics/Stories with keys, points, sprint, status
04 Sprint Plan | 4-day plan with exit criteria
05 AI Prompts | ✓-checkable copy-paste prompts in build order
06 Architecture Checklist | ✓-checkable design-decision gates
07 Data Schema Tasks | Field-by-field scenario/model/output schema
08 Algorithm Breakdown | Step-by-step scheduling algorithm
09 Deployment Checklist | ✓-checkable deploy + submit steps
10 Assumptions | Assumptions for ARCHITECTURE.md

## Progress Dashboard
Progress Dashboard
Auto-calculated from the ✓ Done column on '01 Master Backlog'.
OVERALL
Total tasks | 50
Done | 0
Remaining | 50
Completion % | 0% | ░░░░░░░░░░░░░░░░░░░░
Total est. hours | 137
Hours done | 0
BY EPIC
Epic | Done | Total | % Complete | Progress
A. Setup & Scaffolding | 0 | 5 | 0% | ░░░░░░░░░░
B. Data Model & Schema | 0 | 8 | 0% | ░░░░░░░░░░
C. Scheduling Engine | 0 | 11 | 0% | ░░░░░░░░░░
D. Internal API / Contracts | 0 | 3 | 0% | ░░░░░░░░░░
E. Frontend (Streamlit) | 0 | 5 | 0% | ░░░░░░░░░░
F. Scenario Data | 0 | 2 | 0% | ░░░░░░░░░░
G. Testing | 0 | 6 | 0% | ░░░░░░░░░░
H. Documentation | 0 | 6 | 0% | ░░░░░░░░░░
I. Deployment | 0 | 4 | 0% | ░░░░░░░░░░
BY PRIORITY
Priority | Done | Total | % Complete
P0 | 0 | 39 | 0%
P1 | 0 | 8 | 0%
P2 | 0 | 3 | 0%
FULL PDF REVIEW COVERAGE
All 13 PDF pages reviewed. 47 requirements captured and traced (see '02 Requirements Trace'); 50 build tasks defined. Coverage = 47/47.

## 01 Master Backlog
✓ Done | ID | Epic | Layer | Task | Implementation Prompt (AI-ready) | Acceptance Criteria | Priority | Dependencies | Effort (hrs) | Status | Spec Ref
| A1 | A. Setup & Scaffolding | DevOps / Repo | Initialize repo & folder structure | Create a public-ready Python repo named `bus-charging-scheduler`. Lay out this structure: `app.py` (Streamlit entry), `scheduler/` (engine package), `scheduler/rules/` (pluggable rules), `data/scenarios/` (scenario files), `tests/`, `requirements.txt`, `README.md`, `ARCHITECTURE.md`, `.gitignore` (Python). Add empty `__init__.py` to every package. One repo, one process — no separate services. | Repo tree matches the layout; `python -c 'import scheduler'` works; .gitignore excludes __pycache__, .venv, .streamlit/secrets. | P0 | - | 2 | Not Started | Stack & hosting; Deliverable 2
| A2 | A. Setup & Scaffolding | DevOps / Repo | Author requirements.txt | Create `requirements.txt` pinned to known-good versions: streamlit, pandas. Add `ortools` ONLY if you choose the CP-SAT optimizer path (keep optional). Keep the list minimal so Streamlit Community Cloud installs cleanly from this file. | `pip install -r requirements.txt` succeeds in a clean venv; Streamlit Cloud build reads it automatically. | P0 | A1 | 1 | Not Started | Stack & hosting (requirements.txt)
| A3 | A. Setup & Scaffolding | Backend / Config | Central constants & world config module | Create `scheduler/config.py` holding ONLY physical/world defaults that are not part of a scenario: default SPEED_KMPH=60, CHARGE_MINUTES=25, BATTERY_RANGE_KM=240. Expose as a frozen dataclass `WorldDefaults`. Everything else (route, stations, weights, buses) must come from the scenario file, NOT from here. Document that these are overridable per-scenario. | No magic numbers anywhere else in the codebase; grep for 25/240/60 returns only config.py. | P0 | A1 | 2 | Not Started | Physical constants; tunable/no-hardcode mandate
| A4 | A. Setup & Scaffolding | Docs | README skeleton | Create `README.md` with section stubs: Overview, Live link, Run locally, Project layout, How to change a weight, How to add a new rule, Scenarios, Assumptions. Fill prose later (H1). | All required README sections present as headers. | P2 | A1 | 1 | Not Started | Deliverable: README.md
| A5 | A. Setup & Scaffolding | Docs | ARCHITECTURE skeleton | Create `ARCHITECTURE.md` with stubs: Framework choice & why, Data structure design, Anticipated future changes (table), Change a weight (code example), Add a rule (code example), Assumptions. Fill later (H2-H6). | All required ARCHITECTURE sections present as headers. | P2 | A1 | 1 | Not Started | Deliverable: ARCHITECTURE.md
| B1 | B. Data Model & Schema | Data / Schema | Route & segment model | In `scheduler/model.py` define a `Segment(from_node, to_node, distance_km)` dataclass and a `Route(nodes: list[str], segments: list[Segment])`. Provide `distance_between(node_a, node_b)` and `cumulative_distance(node)`. Route must be data-driven (read from scenario), so changing a segment distance or adding a node is data-only. | Route built from a list of nodes+distances; querying B->C returns 100; adding node 'E' needs no code change. | P0 | A3 | 3 | Not Started | Route table; 'change a segment distance' curveball
| B2 | B. Data Model & Schema | Data / Schema | Station model with charger count | Define `Station(id, node, num_chargers=1)`. Store stations as data on the scenario, keyed by node. `num_chargers` MUST be a field (today=1) so 'double the chargers' is a data edit. Only intermediate nodes (A,B,C,D) are stations; endpoints are not. | Station carries num_chargers; setting num_chargers=2 requires no engine code change (see C7). | P0 | B1 | 2 | Not Started | 1 charger per station; 'double the chargers' curveball
| B3 | B. Data Model & Schema | Data / Schema | Operator model | Define operators as a simple set/registry derived from buses, plus an optional `Operator(id, attributes={})` for future per-operator config (priority, SLA). Do not hardcode the 3 names; derive from data. | Operators discovered from bus list; adding 'newop' is data-only. | P1 | B4 | 1 | Not Started | 3 operators; 'swap in a new operator' curveball
| B4 | B. Data Model & Schema | Data / Schema | Bus model | Define `Bus(id, operator, direction, departure_min, origin, range_km=None, priority=0)`. `direction` is derived from origin/destination via the route, not an enum hardcoded to two values. `range_km` defaults to scenario battery range but is per-bus overridable. `priority` field reserved for future priority-bus rule. | Bus supports per-bus range & priority fields even though scenarios don't use them yet. | P0 | B1 | 3 | Not Started | Buses table; priority buses & variable range (future)
| B5 | B. Data Model & Schema | Data / Schema | Scenario file schema (THE data structure) | Design the scenario file as JSON (or YAML). Top-level keys: `name`, `world` (speed, charge_minutes, battery_range), `route` (nodes + segment distances), `stations` (node -> num_chargers), `weights` (individual, operator, overall + open dict for future weights), `buses` (list). This single file fully describes a situation. Write `data/scenarios/scenario_1.json` as the canonical example and document the schema inline in ARCHITECTURE. | A scenario file alone fully specifies the world; reviewer can read it and understand the input. | P0 | B1,B2,B4 | 4 | Not Started | 'A scenario IS your data structure'; design data first
| B6 | B. Data Model & Schema | Data / Schema | Weights model (open/extensible) | Represent weights as a dict `{individual:1.0, operator:1.0, overall:1.0, ...}` loaded from the scenario, NOT constants. The cost function reads weights by key, so adding a new weighted term = add a key + a rule, no engine edit. Provide a default-merge so missing keys fall back to 1.0. | Changing operator weight to 2.0 is a one-value edit in the scenario JSON; new weight keys are accepted without code change. | P0 | B5 | 2 | Not Started | Tunable weights, one obvious place, not hardcoded
| B7 | B. Data Model & Schema | Data / Schema | Output / result model | Define output dataclasses: `ChargeEvent(station, arrive_min, start_min, wait_min, end_min)`, `BusPlan(bus_id, charge_events:list, arrival_min, total_wait)`, `ScheduleResult(bus_plans:list, station_order:dict[node->list[bus_id]], objective_breakdown:dict)`. This is what the UI renders. | Result object carries everything the per-bus and per-station views need; serializable for debugging. | P0 | B4 | 3 | Not Started | Output: timeline, waits, arrival, station order
| B8 | B. Data Model & Schema | Backend / Loader | Scenario loader + validator | Write `scheduler/loader.py: load_scenario(path) -> Scenario`. Parse JSON into model objects, merge world defaults, validate: distances>0, every bus operator non-empty, departure>=0, route connected, station nodes ⊆ route intermediate nodes. Raise clear errors. Add `list_scenarios(dir)` for the dropdown. | All 5 files load; a malformed file raises a readable ValueError; list_scenarios returns 5 names. | P0 | B5 | 3 | Not Started | Reads any scenario from your data files
| C1 | C. Scheduling Engine | Algorithm / Physics | Travel-time & distance helpers | In `scheduler/physics.py`: `travel_minutes(distance_km, speed_kmph)`, `arrival_time_at(node, bus, route, speed)` returning clock minutes a bus reaches each node assuming no waiting yet. Use consistent speed from world config. Pure functions, fully unit-testable. | 60 km/h over 100 km returns 100 min; arrival at A for a 19:00 BK bus = departure+100. | P0 | B1,B4 | 3 | Not Started | Travel time from distance; consistent speed
| C2 | C. Scheduling Engine | Algorithm / Feasibility | Feasible charging-plan generator | In `scheduler/plans.py: candidate_plans(bus, route, range_km) -> list[list[node]]`. Enumerate ordered subsets of the bus's downstream stations such that no leg (start->first, between charges, last->dest) exceeds range_km, and stations are visited in route order (no backtracking). Return all feasible station-subset plans for the scheduler to choose among. | BK bus (540 km, 240 range) yields only plans with >=2 charges; every returned plan respects the 240 km leg constraint; KB direction enumerates its own station order. | P0 | C1 | 5 | Not Started | 240km rule; >=2 charges for BK; route order; no backtrack
| C3 | C. Scheduling Engine | Backend / Framework | Pluggable Rule base + registry | Create `scheduler/rules/base.py` with an abstract `Rule` (name, kind in {'hard','soft'}, `def evaluate(context) -> float¦bool`). Hard rules return feasibility (bool/inf cost); soft rules return a non-negative penalty. Create a `RuleRegistry` that auto-discovers rule instances. Engine consumes the registry generically — adding a rule = drop a file + register, NO engine edit. | A new rule file added to rules/ is picked up automatically; engine code does not mention specific rule names. | P0 | A3 | 4 | Not Started | Add a new rule without rewriting the engine
| C4 | C. Scheduling Engine | Algorithm / Hard Rules | Implement hard rules | As Rule subclasses: `RangeRule` (no leg > range), `ChargerExclusivityRule` (<= num_chargers buses overlapping at a station), `ChargeDurationRule` (exactly charge_minutes), `RouteOrderRule` (no backtracking). Each is independently testable and registered as kind='hard'. | Each hard rule flags the corresponding violation in a crafted bad schedule; valid schedule passes all. | P0 | C3 | 4 | Not Started | All four hard rules that must always hold
| C5 | C. Scheduling Engine | Algorithm / Soft Rules | Implement weighted soft rules | As Rule subclasses kind='soft': `IndividualWaitRule` (penalty ~ per-bus wait/lateness), `OperatorRule` (penalty ~ variance/total wait within each operator fleet), `OverallRule` (penalty ~ network total time / makespan). Each multiplies its penalty by the matching weight read from scenario weights by key. | Setting operator weight 2.0 measurably increases operator term's influence; each rule reads its own weight key. | P0 | C3,B6 | 5 | Not Started | 3 soft rules; tunable weights drive behavior
| C6 | C. Scheduling Engine | Algorithm / Objective | Weighted objective aggregator | In `scheduler/objective.py: score(schedule, registry, weights) -> (feasible:bool, total_cost:float, breakdown:dict)`. Sum soft penalties * weights; if any hard rule fails -> infeasible. Return per-term breakdown for transparency/debugging and for ARCHITECTURE evidence. | Breakdown sums to total_cost; infeasible schedule reports which hard rule failed. | P0 | C4,C5 | 3 | Not Started | Weigh three soft rules; defensible scoring
| C7 | C. Scheduling Engine | Algorithm / Resource | Charger arbitration (single & multi-charger) | Model each station as a resource with `num_chargers` time-slots of length charge_minutes. `reserve(station, requested_start) -> actual_start` assigns the earliest free charger >= requested_start, computing wait. Generalize over num_chargers so 1 vs 2 chargers is data-only. This resolves 'who goes first, who waits'. | With 1 charger, overlapping requests serialize (second waits); with num_chargers=2 two buses charge concurrently — no code change, only data. | P0 | C4 | 5 | Not Started | One bus per charger; decide order & waits; 'double chargers'
| C8 | C. Scheduling Engine | Algorithm / Core | Core scheduler orchestration | Implement the chosen approach in `scheduler/engine.py: schedule(scenario) -> ScheduleResult`. RECOMMENDED: deterministic, event-driven greedy — process charge requests in time order; for each bus pick the feasible candidate plan + charger ordering that minimizes the weighted objective (C6) given commitments so far; tie-break by bus priority then departure then id. Keep the search strategy swappable (Strategy pattern) so CP-SAT/ILP can replace greedy later without touching rules or data. | Returns a complete ScheduleResult for all buses; deterministic across runs; swapping strategy class doesn't touch rules. | P0 | C2,C6,C7 | 8 | Not Started | Decides plans + order; approach must be defensible & scalable
| C9 | C. Scheduling Engine | Algorithm / Output | Per-bus timeline computation | From engine commitments, build each `BusPlan`: arrival at each station, charge start (after wait), wait minutes, charge end, departure, and final arrival at destination. Compose into ScheduleResult.bus_plans. | Each bus timeline is internally consistent (end=start+charge_minutes; next leg arrival = prev end + travel). | P0 | C8 | 3 | Not Started | Compute per-bus timeline: charge where/when, wait, arrival
| C10 | C. Scheduling Engine | Algorithm / Output | Per-station ordering output | Populate `station_order[node] = [bus_id ...]` sorted by actual charge start time at each station, including which charger index when multi-charger. This feeds the per-station view. | Order at each station matches charge start times; consistent with bus timelines. | P1 | C8 | 2 | Not Started | Per-station view: order buses charged
| C11 | C. Scheduling Engine | Algorithm / Validation | Post-schedule invariant check | After scheduling, run all hard rules over the final ScheduleResult and assert zero violations (defensive double-check). Expose `validate(result, scenario) -> list[Violation]`. Surface any violation loudly (the schedule must never silently break the 240 km rule). | validate() returns [] for all 5 scenarios; deliberately corrupted result returns specific violations. | P0 | C8,C4 | 3 | Not Started | Correctness: schedules respect all hard rules
| D1 | D. Internal API / Contracts | API / Contract | Loader -> Engine contract | Define a clean function boundary: UI/CLI calls `load_scenario(path)` then `schedule(scenario)`. No Streamlit imports inside scheduler package (engine must be usable headless / from tests / future REST API). | Engine importable and runnable with zero Streamlit dependency; `python -m scheduler.engine data/scenarios/scenario_1.json` prints a result. | P1 | B8,C8 | 2 | Not Started | Scalability: engine reusable beyond this UI
| D2 | D. Internal API / Contracts | API / Contract | Engine -> UI result contract | Provide adapters converting ScheduleResult into pandas DataFrames the UI needs: `to_bus_table(result)`, `to_station_table(result, node)`, `to_input_table(scenario)`. Keep formatting (HH:MM) in the adapter, not the engine. | Adapters return tidy DataFrames; engine stays format-agnostic (minutes only). | P1 | C9,C10 | 3 | Not Started | UI renders per-bus & per-station; input table
| D3 | D. Internal API / Contracts | API / Perf | Result caching | Wrap scenario load + schedule in `st.cache_data` keyed by scenario name + weights so re-selecting a scenario is instant and recompute only on change. | Switching scenarios twice triggers compute once; changing a weight invalidates cache. | P2 | D2 | 1 | Not Started | Smooth UX; scalability
| E1 | E. Frontend (Streamlit) | Frontend / UI | App entry, layout & scenario dropdown | In `app.py`: set page config, title, and a `st.selectbox` populated from `list_scenarios()` AT THE TOP so reviewers land on the dropdown immediately. Load the selected scenario and run the scheduler (cached). Use tabs/sections for the three views. | Opening the app shows the dropdown first; selecting a scenario triggers a scheduled result. | P0 | D2,B8 | 3 | Not Started | Dropdown at top; land on app & see it immediately
| E2 | E. Frontend (Streamlit) | Frontend / UI | Scenario input view | Add a section showing the raw input: a readable table of buses (id, operator, direction, departure HH:MM) plus the world/route/stations/weights summary. Optionally show raw JSON in an expander so reviewers see exactly what's fed in. | Reviewer can see the full input for any scenario, including the active weights. | P0 | E1,D2 | 3 | Not Started | Scenario view showing the input
| E3 | E. Frontend (Streamlit) | Frontend / UI | Per-bus timetable view | Render one row (or expandable block) per bus: stations used, arrive/start/wait/end at each, and final arrival time, all HH:MM. Show charge count. Sort by departure. Make waits visually obvious (e.g., highlight non-zero waits). | Every bus shows a complete, readable timeline; BK buses show >=2 charges; waits are visible. | P0 | E1,D2 | 4 | Not Started | Per-bus timetable: stations, time, wait, arrival
| E4 | E. Frontend (Streamlit) | Frontend / UI | Per-station view | For each of A,B,C,D show the ordered list of buses that charged there (bus id, operator, charge start, wait, end, charger index if multi). One table or column per station. | Order at each station is clear and matches the schedule; reviewer can sanity-check fairness vs weights. | P0 | E1,D2 | 3 | Not Started | Per-station view: order buses charged
| E5 | E. Frontend (Streamlit) | Frontend / UI | Live weight controls (optional but recommended) | Add sidebar sliders for individual/operator/overall weights, defaulting to the scenario's values. On change, re-run the scheduler so reviewers can SEE weights change the schedule (esp. Scenario 4). Provide a 'reset to scenario defaults' button. Keep scenario file as source of truth for defaults. | Dragging operator weight up visibly reorders Scenario 4; reset restores file defaults. | P1 | E1,C6 | 3 | Not Started | Different weights -> different defensible schedules
| F1 | F. Scenario Data | Data / Content | Encode all 5 scenarios | Create `data/scenarios/scenario_1..5.json` from the PDF tables. S1 even 15-min spacing; S2 bunched 8-min then spaced; S3 asymmetric (10 BK, 4 KB); S4 operator-heavy (KPN 8/10) with weights individual=1,operator=2,overall=1; S5 worst-case convergence 8-min both ends. All share route/world/240km/25min/1 charger; S1-3,S5 weights default 1/1/1. | All 5 files parse; departure times & operators exactly match the PDF; S4 carries operator=2.0. | P0 | B5,B8 | 4 | Not Started | Ship all 5 scenarios in your data format
| F2 | F. Scenario Data | Data / QA | Validate scheduled output for all 5 | Run engine on each scenario; eyeball per-bus and per-station outputs for sensibility (enough charges, reasonable waits, no range violations). Capture a short notes file of observed behavior per scenario for the interview. | Every scenario produces a sensible, defensible result with zero hard-rule violations. | P0 | F1,C11 | 3 | Not Started | Cycle through all 5; every one sensible
| G1 | G. Testing | Testing / Unit | Physics unit tests | pytest in `tests/test_physics.py`: travel_minutes, arrival times for both directions, speed config respected. | Tests pass; cover both directions and a non-60 speed. | P1 | C1 | 2 | Not Started | Code quality / correctness
| G2 | G. Testing | Testing / Unit | Feasibility/plan tests | `tests/test_plans.py`: assert no candidate plan has a leg >240; BK requires >=2 charges; route order preserved; KB enumerates reversed station order. | All assertions pass; an impossible range (e.g., 90km) yields no plan -> handled. | P0 | C2 | 3 | Not Started | 240 km rule; >=2 charges
| G3 | G. Testing | Testing / Unit | Rule unit tests | `tests/test_rules.py`: each hard rule flags its violation; each soft rule returns higher penalty for worse schedules; weight multiplication correct. | Each rule has at least one positive and one negative test. | P1 | C4,C5 | 3 | Not Started | Scalability: rules independently testable
| G4 | G. Testing | Testing / Invariant | Charger exclusivity invariant test | `tests/test_charger.py`: across a full schedule, no station has more concurrent charges than num_chargers; multi-charger config allows concurrency. | Invariant holds for all 5 scenarios; multi-charger test passes. | P0 | C7,C11 | 2 | Not Started | One bus per charger at a time
| G5 | G. Testing | Testing / E2E | End-to-end scenario tests | `tests/test_e2e.py`: load & schedule each of the 5 scenarios; assert validate()==[] and every BK bus has >=2 charges and every bus arrives. | All 5 scenarios green end-to-end. | P0 | C11,F1 | 3 | Not Started | Correctness across all scenarios
| G6 | G. Testing | Testing / Behavior | Weight-sensitivity test | `tests/test_weights.py`: run Scenario 4 with operator weight 1.0 vs 2.0 and assert the resulting station order / objective breakdown differs in the operator term. | Different weights produce a measurably different, defensible schedule. | P1 | C6,F1 | 2 | Not Started | Different weights -> different schedules
| H1 | H. Documentation | Docs | README full write-up | Fill README: one-line overview, live Streamlit link, `streamlit run app.py` instructions, venv + pip steps, project layout, exactly how to change a weight (point to scenario JSON + sidebar), how to add a rule (point to rules/ + 5-line example), scenario list, assumptions link. | A new dev can clone, install, run, change a weight, and add a rule using only the README. | P0 | A4,E5,C3 | 3 | Not Started | Deliverable: README (run, change weight, add rule)
| H2 | H. Documentation | Docs | ARCHITECTURE: framework choice & why | Explain the chosen approach (event-driven greedy + pluggable weighted rule registry, Strategy-swappable to CP-SAT). Justify fit: small instances, need for easy rule addition and weight tuning, deterministic & explainable output, no heavy solver dependency. Contrast with pure ILP/CP-SAT (more optimal, heavier, harder to extend rules ad hoc) and note migration path. | Reviewer understands why this approach fits and how it scales; trade-offs are explicit. | P0 | A5,C8 | 3 | Not Started | Docs: framework & why it's the right fit
| H3 | H. Documentation | Docs | ARCHITECTURE: anticipated future changes table | Write the change-foresight table: for each anticipated change state how the design absorbs it WITHOUT code changes. Cover: add a station; change a segment distance; double/var chargers per station; swap/add operator; add/remove buses; new route / multiple routes sharing stations; priority buses; time-of-day electricity cost; driver shifts; partial/variable charge time; variable speed/traffic; per-bus battery range; new soft or hard rule; new weighted objective term; bigger fleets (perf). | Breadth & specificity is high; each row names the exact field/file that changes (data) vs claims 'no engine rewrite'. | P0 | A5,B5,C3 | 4 | Not Started | KEY SIGNAL: breadth of anticipated changes
| H4 | H. Documentation | Docs | ARCHITECTURE: change-a-weight example | Show the literal diff: edit `weights.operator` from 1.0 to 2.0 in the scenario JSON (and/or sidebar slider). Explain the cost function reads weights by key, no code touched. | Concrete before/after snippet; verifiably one-value change. | P0 | A5,B6 | 1 | Not Started | Docs: how to change a weight w/ example
| H5 | H. Documentation | Docs | ARCHITECTURE: add-a-rule example | Show a full minimal new rule (e.g., `ElectricityCostRule` penalizing charging during a peak window) as a ~10-line Rule subclass dropped into rules/, plus the one-line weight key added to scenarios. Demonstrate the engine needs no edit. | A reader could paste the example and have a working new soft rule. | P0 | A5,C3 | 2 | Not Started | Docs: how to add a rule w/ example; live add-rule test
| H6 | H. Documentation | Docs | ARCHITECTURE: assumptions log | Document every assumption: speed=60 km/h; charging always to full & exactly 25 min; buses don't charge at endpoints; instantaneous decision/no re-planning mid-trip; ties broken by priority->departure->id; objective definitions for each soft term; what 'operator runs smoothly' means quantitatively; behavior if no feasible plan exists; whether buses may skip optional charges. Be honest about what's not done. | Assumptions are explicit and defensible; gaps in the spec are addressed. | P0 | A5 | 2 | Not Started | Make your own calls; document assumptions
| I1 | I. Deployment | DevOps / Deploy | Push public GitHub repo | Create a PUBLIC GitHub repo, push all code, data/scenarios, tests, README, ARCHITECTURE. Ensure no secrets committed. Add a clear commit history. | Repo is public and contains all code + all 5 scenarios + both docs. | P0 | H1,F1 | 1 | Not Started | Deliverable: public GitHub repo
| I2 | I. Deployment | DevOps / Deploy | Deploy to Streamlit Community Cloud | Connect the repo on share.streamlit.io, set main file `app.py`, deploy. Confirm requirements.txt installs and app boots on the dropdown. | Public Streamlit URL loads and shows the scenario dropdown. | P0 | I1,A2,E1 | 2 | Not Started | Deliverable: hosted public link
| I3 | I. Deployment | DevOps / QA | Hosted smoke test (all 5) | On the live URL, cycle all 5 scenarios; confirm input view, per-bus timetable, per-station view all render and look sensible; test on a fresh browser/incognito. | All 5 scenarios render correctly on the hosted app for an anonymous visitor. | P0 | I2,F2 | 1 | Not Started | How we'll test: cycle through all 5
| I4 | I. Deployment | PM / Submit | Submit the form | Submit hosted URL + repo URL + approach summary + build notes via the Google Form. Re-submit if anything changes (latest wins). Deadline June 2nd. | Form submitted with both public URLs and a crisp approach summary. | P0 | I2,I1 | 1 | Not Started | Submission form; deadline June 2
[8 empty] | DONE / TOTAL: | 0 / 50
[8 empty] | TOTAL HOURS: | 137

## 02 Requirements Trace
✓ Done | Req ID | Requirement (from PDF) | Source | Covered by Task(s)
| R1 | Python + Streamlit, one repo, one process | p1 | A1,A2,E1
| R2 | Host on Streamlit Community Cloud (public) | p1 | I2,I3
| R3 | requirements.txt auto-installed | p1 | A2
| R4 | Route Bengaluru-A-B-C-D-Kochi, segments 100/120/100/120/100 | p2 | B1,F1
| R5 | Bidirectional buses share stations | p1 | B4,C7
| R6 | Start full charge, 240 km range | p1 | A3,B4,C2
| R7 | Only A,B,C,D scheduled; endpoints not | p1 | B2,C2
| R8 | 1 charger per station | p2 | B2,C7
| R9 | Charging always to full, exactly 25 min | p2 | A3,C4
| R10 | Travel time from distance, consistent speed | p2 | A3,C1
| R11 | 20 buses (10 BK + 10 KB) per scenario | p2 | B4,F1
| R12 | Each bus has departure time | p2 | B4,F1
| R13 | 3 operators KPN/Freshbus/Flixbus | p2 | B3,F1
| R14 | No leg > 240 km else invalid | p2 | C2,C4,G2
| R15 | BK trip needs >= 2 charges | p2 | C2,G2
| R16 | HARD: one bus per charger at a time | p3 | C7,G4
| R17 | HARD: charge exactly 25 min | p3 | C4
| R18 | HARD: never run out of range | p3 | C2,C4,C11
| R19 | HARD: stations in route order, no backtrack | p3 | C2,C4
| R20 | SOFT: individual bus wait minimized | p3 | C5
| R21 | SOFT: operator fleet runs smoothly | p3 | C5
| R22 | SOFT: overall network time low | p3 | C5
| R23 | Weights tunable, not hardcoded, one place | p3 | A3,B6,H4
| R24 | Add a new rule without rewriting engine | p3 | C3,H5
| R25 | Grow world (buses/stations/operators/routes) no rewrite | p3 | B1,B2,B5,H3
| R26 | Scenario IS the data structure; design it | p4 | B5,H3
| R27 | Ship all 5 scenarios encoded | p4 | F1
| R28 | Default weights 1/1/1 except S4 operator=2.0 | p5 | B6,F1
| R29 | Scheduler reads any scenario from data files | p9 | B8,E1
| R30 | Decide charging plan + station order | p9 | C2,C8,C10
| R31 | Compute per-bus timeline (charge where/when, wait, arrival) | p9 | C9,E3
| R32 | UI: scenario dropdown at top | p9 | E1
| R33 | UI: scenario input view | p10 | E2
| R34 | UI: per-bus timetable | p10 | E3
| R35 | UI: per-station view | p10 | E4
| R36 | No dashboards/maps/animations | p10 | E1
| R37 | Land on app -> see dropdown immediately | p10 | E1,I3
| R38 | Deliverable: hosted link | p10 | I2
| R39 | Deliverable: public GitHub repo | p11 | I1
| R40 | README (run, change weight, add rule) | p11 | H1
| R41 | ARCHITECTURE (framework+why, data design, anticipated changes, weight/rule examples, assumptions) | p11 | H2,H3,H4,H5,H6
| R42 | Make & document assumptions | p10 | H6
| R43 | In-memory state fine; no auth/DB/maps | p11 | A1,D3
| R44 | Correctness: respect 240km; weights->different schedules | p11 | C11,G5,G6
| R45 | Live: encode a fresh scenario | p12 | B5,F1
| R46 | Live: extend data (new station, +chargers, new operator, segment dist) | p12 | B1,B2,B3,H3
| R47 | Live: add a new soft/hard rule | p12 | C3,H5

## 03 Jira Backlog
Issue Type | Key | Summary | Epic Link | Story Points | Priority | Sprint | Labels | Status
Epic | BCS-1 | Project setup & scaffolding |  |  | P0 |  | epic | To Do
Epic | BCS-2 | Domain data model & scenario schema |  |  | P0 |  | epic | To Do
Epic | BCS-3 | Scheduling engine & algorithm |  |  | P0 |  | epic | To Do
Epic | BCS-4 | Internal API / contracts |  |  | P0 |  | epic | To Do
Epic | BCS-5 | Streamlit UI |  |  | P0 |  | epic | To Do
Epic | BCS-6 | Scenario data (5 scenarios) |  |  | P0 |  | epic | To Do
Epic | BCS-7 | Testing & invariants |  |  | P0 |  | epic | To Do
Epic | BCS-8 | Documentation (README + ARCHITECTURE) |  |  | P0 |  | epic | To Do
Epic | BCS-9 | Deployment & submission |  |  | P0 |  | epic | To Do
Story | BCS-101 | [A1] Initialize repo & folder structure | BCS-1 | 2 | P0 | Day 1 | devops | To Do
Story | BCS-102 | [A2] Author requirements.txt | BCS-1 | 1 | P0 | Day 1 | devops | To Do
Story | BCS-103 | [A3] Central constants & world config module | BCS-1 | 2 | P0 | Day 1 | backend | To Do
Story | BCS-104 | [A4] README skeleton | BCS-1 | 1 | P2 | Day 1 | docs | To Do
Story | BCS-105 | [A5] ARCHITECTURE skeleton | BCS-1 | 1 | P2 | Day 1 | docs | To Do
Story | BCS-106 | [B1] Route & segment model | BCS-2 | 3 | P0 | Day 1 | data | To Do
Story | BCS-107 | [B2] Station model with charger count | BCS-2 | 2 | P0 | Day 1 | data | To Do
Story | BCS-108 | [B3] Operator model | BCS-2 | 1 | P1 | Day 1 | data | To Do
Story | BCS-109 | [B4] Bus model | BCS-2 | 3 | P0 | Day 1 | data | To Do
Story | BCS-110 | [B5] Scenario file schema (THE data structure) | BCS-2 | 5 | P0 | Day 1 | data | To Do
Story | BCS-111 | [B6] Weights model (open/extensible) | BCS-2 | 2 | P0 | Day 1 | data | To Do
Story | BCS-112 | [B7] Output / result model | BCS-2 | 3 | P0 | Day 1 | data | To Do
Story | BCS-113 | [B8] Scenario loader + validator | BCS-2 | 3 | P0 | Day 1 | backend | To Do
Story | BCS-114 | [C1] Travel-time & distance helpers | BCS-3 | 3 | P0 | Day 2 | algorithm | To Do
Story | BCS-115 | [C2] Feasible charging-plan generator | BCS-3 | 5 | P0 | Day 2 | algorithm | To Do
Story | BCS-116 | [C3] Pluggable Rule base + registry | BCS-3 | 5 | P0 | Day 2 | backend | To Do
Story | BCS-117 | [C4] Implement hard rules | BCS-3 | 5 | P0 | Day 2 | algorithm | To Do
Story | BCS-118 | [C5] Implement weighted soft rules | BCS-3 | 5 | P0 | Day 2 | algorithm | To Do
Story | BCS-119 | [C6] Weighted objective aggregator | BCS-3 | 3 | P0 | Day 2 | algorithm | To Do
Story | BCS-120 | [C7] Charger arbitration (single & multi-charger) | BCS-3 | 5 | P0 | Day 2 | algorithm | To Do
Story | BCS-121 | [C8] Core scheduler orchestration | BCS-3 | 8 | P0 | Day 2 | algorithm | To Do
Story | BCS-122 | [C9] Per-bus timeline computation | BCS-3 | 3 | P0 | Day 2 | algorithm | To Do
Story | BCS-123 | [C10] Per-station ordering output | BCS-3 | 2 | P1 | Day 2 | algorithm | To Do
Story | BCS-124 | [C11] Post-schedule invariant check | BCS-3 | 3 | P0 | Day 2 | algorithm | To Do
Story | BCS-125 | [D1] Loader -> Engine contract | BCS-4 | 2 | P1 | Day 2 | api | To Do
Story | BCS-126 | [D2] Engine -> UI result contract | BCS-4 | 3 | P1 | Day 2 | api | To Do
Story | BCS-127 | [D3] Result caching | BCS-4 | 1 | P2 | Day 2 | api | To Do
Story | BCS-128 | [E1] App entry, layout & scenario dropdown | BCS-5 | 3 | P0 | Day 3 | frontend | To Do
Story | BCS-129 | [E2] Scenario input view | BCS-5 | 3 | P0 | Day 3 | frontend | To Do
Story | BCS-130 | [E3] Per-bus timetable view | BCS-5 | 5 | P0 | Day 3 | frontend | To Do
Story | BCS-131 | [E4] Per-station view | BCS-5 | 3 | P0 | Day 3 | frontend | To Do
Story | BCS-132 | [E5] Live weight controls (optional but recommended) | BCS-5 | 3 | P1 | Day 3 | frontend | To Do
Story | BCS-133 | [F1] Encode all 5 scenarios | BCS-6 | 5 | P0 | Day 3 | data | To Do
Story | BCS-134 | [F2] Validate scheduled output for all 5 | BCS-6 | 3 | P0 | Day 3 | data | To Do
Story | BCS-135 | [G1] Physics unit tests | BCS-7 | 2 | P1 | Day 4 | testing | To Do
Story | BCS-136 | [G2] Feasibility/plan tests | BCS-7 | 3 | P0 | Day 4 | testing | To Do
Story | BCS-137 | [G3] Rule unit tests | BCS-7 | 3 | P1 | Day 4 | testing | To Do
Story | BCS-138 | [G4] Charger exclusivity invariant test | BCS-7 | 2 | P0 | Day 4 | testing | To Do
Story | BCS-139 | [G5] End-to-end scenario tests | BCS-7 | 3 | P0 | Day 4 | testing | To Do
Story | BCS-140 | [G6] Weight-sensitivity test | BCS-7 | 2 | P1 | Day 4 | testing | To Do
Story | BCS-141 | [H1] README full write-up | BCS-8 | 3 | P0 | Day 4 | docs | To Do
Story | BCS-142 | [H2] ARCHITECTURE: framework choice & why | BCS-8 | 3 | P0 | Day 4 | docs | To Do
Story | BCS-143 | [H3] ARCHITECTURE: anticipated future changes table | BCS-8 | 5 | P0 | Day 4 | docs | To Do
Story | BCS-144 | [H4] ARCHITECTURE: change-a-weight example | BCS-8 | 1 | P0 | Day 4 | docs | To Do
Story | BCS-145 | [H5] ARCHITECTURE: add-a-rule example | BCS-8 | 2 | P0 | Day 4 | docs | To Do
Story | BCS-146 | [H6] ARCHITECTURE: assumptions log | BCS-8 | 2 | P0 | Day 4 | docs | To Do
Story | BCS-147 | [I1] Push public GitHub repo | BCS-9 | 1 | P0 | Day 4 | devops | To Do
Story | BCS-148 | [I2] Deploy to Streamlit Community Cloud | BCS-9 | 2 | P0 | Day 4 | devops | To Do
Story | BCS-149 | [I3] Hosted smoke test (all 5) | BCS-9 | 1 | P0 | Day 4 | devops | To Do
Story | BCS-150 | [I4] Submit the form | BCS-9 | 1 | P0 | Day 4 | pm | To Do

## 04 Sprint Plan
Day | Focus | Tasks | Deliverable | Exit Criteria
Day 1 | Data model first (the foundation) | A1, A2, A3, B1, B2, B3, B4, B5, B6, B7, B8 | Scenario JSON schema + loader; all model objects; world config | scenario_1.json loads into validated model objects via load_scenario()
Day 2 | Engine + algorithm + rules | C1, C2, C3, C4, C5, C6, C7, C8, C9, C10, C11, D1 | Working headless scheduler producing valid ScheduleResult | `python -m scheduler.engine scenario_1.json` returns a valid, validated schedule
Day 3 | UI + all scenarios + adapters | D2, D3, E1, E2, E3, E4, E5, F1, F2 | Full Streamlit app; all 5 scenarios encoded & sensible | App runs locally; dropdown cycles 5 scenarios with 3 views each
Day 4 | Tests, docs, deploy, submit | G1-G6, H1-H6, I1, I2, I3, I4 | Green tests; README + ARCHITECTURE; hosted link; form submitted | Public Streamlit URL + public repo submitted before June 2

## 05 AI Prompts
✓ Done | # | Target File | Component | Copy-Paste Prompt for Claude / Cursor / Windsurf
| 1 | scheduler/config.py | World config | Create scheduler/config.py. Define a frozen dataclass WorldDefaults with fields speed_kmph:float=60, charge_minutes:int=25, battery_range_km:int=240. These are ONLY fallback defaults; every value can be overridden per-scenario. Do not put route, stations, operators, or weights here. Export a module-level DEFAULTS = WorldDefaults(). No other magic numbers may exist anywhere else in the project.
| 2 | scheduler/model.py | Domain model | Create scheduler/model.py with dataclasses: Segment(from_node:str,to_node:str,distance_km:float); Route(nodes:list[str], segments:list[Segment]) with methods distance_between(a,b) and cumulative_distance(node) and downstream_stations(origin, station_nodes) honoring route order for either direction (no backtracking); Station(node:str, num_chargers:int=1); Bus(id:str, operator:str, origin:str, destination:str, departure_min:int, range_km:float¦None=None, priority:int=0) with a derived direction property; Weights as a dict-backed class merging defaults (individual/operator/overall=1.0) with an open dict so unknown keys are allowed; Scenario(name, world:WorldDefaults, route:Route, stations:dict[str,Station], weights, buses:list[Bus]). Keep it pure-Python, no Streamlit import.
| 3 | scheduler/loader.py | Scenario loader | Create scheduler/loader.py. load_scenario(path)->Scenario reads JSON of shape {name, world:{speed_kmph,charge_minutes,battery_range_km}, route:{nodes:[...], segments:[{from,to,distance_km}...]}, stations:{NODE:{num_chargers}}, weights:{individual,operator,overall, ...}, buses:[{id,operator,origin,destination,departure_min,range_km?,priority?}]}. Merge world with config.DEFAULTS for missing keys; default per-bus range_km to battery_range_km. Validate: positive distances, connected route, station nodes are intermediate route nodes, non-empty operators, departure_min>=0. Raise ValueError with a clear message on any failure. Also list_scenarios(dir)->list[(name,path)] for the dropdown.
| 4 | scheduler/physics.py | Physics helpers | Create scheduler/physics.py with pure functions: travel_minutes(distance_km, speed_kmph)->float; node_sequence(bus, route)->list[str] the ordered nodes the bus passes (respecting direction, no backtracking); base_arrival_minutes(bus, route, speed)->dict[node->float] the clock-minute the bus would reach each node with zero charging/waiting. Add the charge_minutes offset logic later in the engine, keep these wait-free. Fully unit-testable, no side effects.
| 5 | scheduler/plans.py | Feasible plan generator | Create scheduler/plans.py: candidate_plans(bus, route, station_nodes, range_km)->list[list[str]]. Enumerate ordered subsets of the bus's downstream station nodes (route order, no backtracking) such that every leg — origin->first charge, charge->next charge, last charge->destination — is <= range_km. Return every feasible plan (the engine will choose among them). If none feasible, return [] (caller handles).
| 6 | scheduler/rules/base.py | Rule framework | Create scheduler/rules/base.py. Define abstract Rule with attributes name:str and kind:Literal['hard','soft'] and method evaluate(ctx)->float where ctx is a ScheduleContext exposing the candidate schedule, scenario, and weights. Hard rules return 0.0 if satisfied else math.inf. Soft rules return a non-negative penalty already multiplied by their weight = ctx.weights[self.weight_key]. Define a RuleRegistry that collects Rule instances; add register() decorator and discover() that imports all modules in scheduler/rules/ so dropping a new rule file auto-registers it. The engine must never reference concrete rule classes by name.
| 7 | scheduler/rules/hard_rules.py | Hard rules | Create scheduler/rules/hard_rules.py with Rule subclasses (kind='hard'), each @register: RangeRule (no leg in any bus plan exceeds bus.range_km); ChargerExclusivityRule (at every station, count of buses whose [start,end] charge intervals overlap never exceeds station.num_chargers); ChargeDurationRule (every charge interval length == world.charge_minutes); RouteOrderRule (each bus's charge stations appear in route order, no repeats/backtrack). Return math.inf on violation else 0.0. No engine edits required to add these.
| 8 | scheduler/rules/soft_rules.py | Soft rules | Create scheduler/rules/soft_rules.py with Rule subclasses (kind='soft'), each @register and each with a weight_key: IndividualWaitRule(weight_key='individual') -> sum (or max) of per-bus total wait/lateness; OperatorRule(weight_key='operator') -> sum over operators of intra-fleet wait variance or total fleet wait (define and document the metric); OverallRule(weight_key='overall') -> network makespan or total travel+wait time. Each returns penalty * ctx.weights[weight_key]. Keep metrics simple, monotonic, and documented in a docstring.
| 9 | scheduler/objective.py | Objective aggregator | Create scheduler/objective.py: score(schedule, scenario, registry)->(feasible:bool, total:float, breakdown:dict). Evaluate all hard rules; if any returns inf -> feasible False. Sum soft-rule penalties into total and record each rule's contribution in breakdown for transparency. Return the tuple.
| 10 | scheduler/resources.py | Charger arbitration | Create scheduler/resources.py: a ChargerPool(num_chargers, charge_minutes) maintaining busy intervals per charger. reserve(requested_start)->(actual_start, charger_index, wait) assigns the earliest charger free at or after requested_start; if all busy, queue behind the earliest-finishing one. Must generalize over num_chargers so 1 vs N differs only by the constructor arg. Provide a per-station pool keyed by node.
| 11 | scheduler/engine.py | Core scheduler | Create scheduler/engine.py: schedule(scenario)->ScheduleResult using a deterministic event-driven greedy strategy behind a Strategy interface (class GreedyStrategy; allow future CpSatStrategy). Process buses in order of (priority desc, departure asc, id). For each bus, evaluate its candidate_plans; for each plan simulate charger reservations via ChargerPool and compute the incremental weighted objective using the rule registry; commit the plan+reservations with the lowest feasible cost. Build BusPlan timelines and station_order. Return ScheduleResult(bus_plans, station_order, objective_breakdown). Keep deterministic. Expose a __main__ that loads a scenario path argv and prints the result. No Streamlit import.
| 12 | scheduler/validate.py | Invariant checker | Create scheduler/validate.py: validate(result, scenario)->list[Violation]. Re-run all hard rules over the FINAL committed schedule and collect any violations as Violation(rule, bus_id_or_station, detail). Used both in tests and at app startup as a defensive guard. Must return [] for a correct schedule.
| 13 | scheduler/adapters.py | UI adapters | Create scheduler/adapters.py: to_input_table(scenario)->DataFrame (bus rows with HH:MM departure + summary of world/route/stations/weights); to_bus_table(result, scenario)->DataFrame (one row per bus: stations used, per-stop arrive/start/wait/end HH:MM, charge count, final arrival HH:MM); to_station_table(result, node)->DataFrame (ordered buses at a node: bus, operator, charger idx, start, wait, end). Add a minutes_to_hhmm helper. Engine returns minutes; formatting lives only here.
| 14 | app.py | Streamlit app | Create app.py. st.set_page_config(title='Bus Charging Scheduler', layout='wide'). At the very top render st.selectbox of list_scenarios() so the dropdown is the first thing visible. On selection, load_scenario + schedule (wrapped in st.cache_data keyed by name+weights). Sidebar sliders for individual/operator/overall weights default to scenario weights with a 'reset to defaults' button; changing them re-runs. Then three sections via st.tabs: 'Input' (to_input_table + raw JSON expander), 'Per-bus timetable' (to_bus_table, highlight non-zero waits, show charge count), 'Per-station' (a to_station_table per node A,B,C,D). At startup run validate() and st.error any violation. No maps/animations/metric dashboards.
| 15 | data/scenarios/*.json | Scenario files | Create data/scenarios/scenario_1.json..scenario_5.json matching the PDF exactly. Shared: route nodes [Bengaluru,A,B,C,D,Kochi] with segment distances 100,120,100,120,100; world speed_kmph 60, charge_minutes 25, battery_range_km 240; stations A,B,C,D each num_chargers 1; departure_min as minutes-from-midnight (19:00=1140). S1: 10 BK + 10 KB every 15 min from 1140, weights 1/1/1. S2: bunched every 8 min first 50 min then spaced, per PDF. S3: 10 BK (15 min) + only 4 KB at 1140/1175/1210/1245. S4: KPN 8 of 10 BK, weights individual 1.0 operator 2.0 overall 1.0. S5: all 20 every 8 min both ends from 1140. Use exact operators/directions/times from the PDF tables.
| 16 | tests/ | Test suite | Create pytest suite under tests/: test_physics.py, test_plans.py (no leg>240, BK>=2 charges, route order, KB reversed), test_rules.py (each rule positive+negative), test_charger.py (concurrency never exceeds num_chargers; multi-charger allows overlap), test_e2e.py (all 5 scenarios: validate()==[] and every BK bus >=2 charges and all arrive), test_weights.py (Scenario 4 operator weight 1.0 vs 2.0 produces different station_order/objective). Use the public loader+engine API only.
| 17 | README.md | README | Write README.md: overview, live Streamlit link placeholder, quickstart (python -m venv, pip install -r requirements.txt, streamlit run app.py), project layout tree, 'Change a weight' (edit weights in the scenario JSON or drag the sidebar slider — one value), 'Add a rule' (drop a Rule subclass in scheduler/rules/, add a weight key — show a 10-line example), scenario descriptions, link to ARCHITECTURE and assumptions.
| 18 | ARCHITECTURE.md | ARCHITECTURE | Write ARCHITECTURE.md covering: (1) Framework choice — event-driven greedy + pluggable weighted rule registry, Strategy-swappable to CP-SAT — and why it fits (small instances, easy rule addition, trivial weight tuning, deterministic explainable output, no heavy solver dep) with trade-offs vs ILP/CP-SAT. (2) Data structure design — annotated scenario JSON schema and the model+result objects. (3) Anticipated future changes table (add station, change segment distance, multi/variable chargers, swap/add operator, +buses, new/multiple routes sharing stations, priority buses, time-of-day electricity cost, driver shifts, partial/variable charge time, variable speed/traffic, per-bus range, new soft/hard rule, new weighted term, large fleets) each mapped to the exact field/file that changes with NO engine rewrite. (4) Change a weight — concrete code/JSON diff. (5) Add a rule — full ~10-line example. (6) Assumptions log. Be honest about what is and isn't done.

## 06 Architecture Checklist
✓ Done | Design Item | Why it matters
| Engine has ZERO Streamlit imports | Engine reusable headless / future REST / tests
| All physical constants live only in config.py | No-hardcode mandate; one obvious place
| Weights read by key from scenario, never constants | Weight tunability is the graded criterion
| Route is data-driven (nodes + segment distances) | 'change a segment distance' must be data-only
| Station carries num_chargers field (today=1) | 'double the chargers' must be data-only
| Direction derived from origin/destination, not a 2-value enum | Multiple routes / new endpoints later
| Operators derived from data, not hardcoded list | 'swap in a new operator' data-only
| Bus has priority & per-bus range_km fields (unused today) | priority buses & variable range anticipated
| Rules are auto-discovered from rules/ directory | Add a rule without engine edit (graded live)
| Hard vs soft rule distinction is explicit (kind field) | Clean extensibility; feasibility vs penalty
| Objective returns a per-term breakdown | Explainability + defend schedules in interview
| Search strategy behind a Strategy interface | Swap greedy -> CP-SAT without touching rules/data
| Charger pool generalizes over num_chargers | 1 vs N chargers is constructor-only
| Post-schedule validate() asserts hard rules | Correctness guard; never silently break 240 km
| Scenario file fully self-describes the world | 'a scenario IS your data structure'
| Result model carries everything the UI needs | Clean engine<->UI contract
| Deterministic output (stable tie-breaks) | Reproducible demos & tests
| st.cache_data on load+schedule | Smooth UX, scales to bigger inputs

## 07 Data Schema Tasks
Entity | Field | Type | Required | Notes / Foresight
Scenario | name | string | yes | Human label shown in dropdown
Scenario | world | object | yes | Overrides config defaults per-scenario
Scenario | route | object | yes | nodes + segments; fully data-driven
Scenario | stations | object | yes | map node -> {num_chargers}
Scenario | weights | object | yes | individual/operator/overall + open keys
Scenario | buses | array | yes | list of Bus objects
world | speed_kmph | number | no (default 60) | Consistent sim speed
world | charge_minutes | number | no (default 25) | Fixed full-charge time
world | battery_range_km | number | no (default 240) | Default per-bus range
route | nodes | array<string> | yes | Ordered incl. endpoints, e.g. [Bengaluru,A,B,C,D,Kochi]
route | segments | array<obj> | yes | {from,to,distance_km}; sums to 540 today
station | node | string | yes | Must be an intermediate route node
station | num_chargers | int | no (default 1) | Make 'double chargers' data-only
weights | individual | float | no (default 1.0) | Per-bus wait penalty weight
weights | operator | float | no (default 1.0) | Operator-fairness weight (S4=2.0)
weights | overall | float | no (default 1.0) | Network-time weight
weights | <future keys> | float | no | e.g. electricity_cost, driver_shift — open dict
bus | id | string | yes | e.g. bus-BK-01
bus | operator | string | yes | kpn/freshbus/flixbus (data-driven)
bus | origin | string | yes | Bengaluru or Kochi (or future endpoints)
bus | destination | string | yes | Defines direction via route
bus | departure_min | int | yes | Minutes from midnight (19:00=1140)
bus | range_km | float | no (default world range) | Per-bus override for variable fleets
bus | priority | int | no (default 0) | Reserved for priority-bus rule
ChargeEvent (output) | station | string | yes | Node where charge happens
ChargeEvent (output) | arrive_min/start_min/wait_min/end_min | int | yes | Full per-stop timing
ChargeEvent (output) | charger_index | int | yes | Which charger (for multi-charger)
BusPlan (output) | bus_id/charge_events/arrival_min/total_wait | mixed | yes | Per-bus timetable source
ScheduleResult (output) | bus_plans/station_order/objective_breakdown | mixed | yes | Drives both UI views + transparency

## 08 Algorithm Breakdown
Step | Description | Inputs | Outputs | Complexity Note
1. Parse & validate | Load scenario JSON into model objects; merge world defaults; validate route/range/stations | scenario file | validated Scenario | O(buses+segments)
2. Compute base arrivals | For each bus, wait-free arrival minute at every node it passes (direction-aware) | Scenario, speed | dict bus->node->minute | O(buses*nodes)
3. Enumerate feasible plans | Per bus, all ordered station subsets with every leg <= range_km, route order only | route, range, stations | candidate plans per bus | O(buses*2^stations) — fine for small station counts; prune by range
4. Order buses | Sort by (priority desc, departure asc, id) for deterministic greedy commitment | buses | processing order | O(buses log buses)
5. Greedy commit | For each bus, for each candidate plan, simulate charger reservations & compute incremental weighted objective; commit cheapest feasible plan | plans, ChargerPool, rules, weights | committed reservations | O(buses*plans*stations)
6. Charger reservation | Earliest free charger >= requested arrival; else queue behind earliest finisher; compute wait; generalizes to num_chargers | ChargerPool state | actual_start, wait, charger idx | O(num_chargers) per reserve
7. Build timelines | Assemble BusPlan per bus: arrive/start/wait/end per stop + final arrival | committed reservations | bus_plans | O(buses*stations)
8. Build station order | Per node, sort charging buses by actual start (+charger idx) | reservations | station_order | O(charges log charges)
9. Validate invariants | Re-run all hard rules on final schedule; assert none violated | ScheduleResult | [] or violations | O(buses*stations)
10. Adapt for UI | Convert result to DataFrames with HH:MM formatting | ScheduleResult | DataFrames | O(rows)
(swap path) | Replace GreedyStrategy with CpSatStrategy implementing same interface for true optimization at larger scale | same scenario | optimal-ish ScheduleResult | solver-dependent — rules & data unchanged

## 09 Deployment Checklist
✓ Done | Step | Action
| 1 | Create PUBLIC GitHub repo and push all code
| 2 | Confirm data/scenarios has all 5 JSON files
| 3 | Confirm README.md and ARCHITECTURE.md committed
| 4 | Confirm requirements.txt lists streamlit + pandas (+ortools if used)
| 5 | Verify no secrets / .streamlit/secrets committed
| 6 | Sign in to share.streamlit.io with GitHub
| 7 | New app -> select repo, branch main, main file app.py
| 8 | Deploy; watch build log install requirements.txt
| 9 | Open hosted URL; confirm dropdown shows on load
| 10 | Cycle all 5 scenarios; check 3 views each render
| 11 | Test in incognito (anonymous public access works)
| 12 | Run pytest locally; all green
| 13 | Final commit; confirm repo still public
| 14 | Submit Google Form: hosted URL + repo URL + approach + notes
| 15 | Re-submit form if anything changes (latest wins) before June 2

## 10 Assumptions
Topic | Assumption | Justification
Speed | Constant 60 km/h all buses, all segments — no traffic/variation | Spec example; tunable in world config
Charging | Always to full, exactly 25 min, no partial charging | Spec hard rule
Endpoints | Buses leave full and do not charge at Bengaluru/Kochi | Spec: endpoints not scheduled
Departure encoding | departure_min = minutes from midnight (19:00=1140) | Clean integer math; HH:MM only in UI
Tie-breaking | priority desc -> departure asc -> bus id | Deterministic, reproducible demos
Plan choice | Bus may use MORE than the minimum charges if cheaper overall | Spec allows '2 or more'
Individual metric | Per-bus total wait (sum of charger waits) | Definition documented; tunable
Operator metric | Total/variance of wait within each operator fleet | Definition documented; tunable
Overall metric | Network makespan or total time across all buses | Definition documented; tunable
Infeasibility | If a bus has no feasible plan, surface a clear error | Shouldn't occur with given data
Re-planning | Decided once up front; no mid-trip re-optimization | Static schedule per spec
State | In-memory only; no DB/auth | Spec: in-memory fine